GBV Rapid Assessment CHECKLIST

| Staff |  |
| --- | --- |
|  | Team Coordinator: Leads in monitoring quality of the assessment as well as analysis and compilation of information |
|  | Team Leader(s): Leads field teams in the implementation of the assessment, working closely with other team leaders, translators and the team coordinator |
|  | Translator(s): Each team leader will have a translator identified from the local community who will be briefed on his/her role in the assessment beforehand; they will also be oriented on codes of conduct, and be clear about their ToR (including payment, working hours, etc.) before the assessment |
|  | Transcriber: Transcribers from the local community will help with translating and transferring information from the assessment forms into a compiled database |
|  | Driver(s): Drivers will be identified within the organization or on a contractual basis and will be briefed on the purpose of the assessment and codes of conduct; every effort will be made to keep the same drivers throughout the entire assessment period |
| Communication |  |
|  | Mobile Phones: Each staff will have one charged phone with substantial credit that they will use throughout the assessment |
|  | Communication Tree: Clear lines of communication in case of security concerns and for general reporting; each team member will share their phone numbers with one another before the assessment commences; the team coordinator (or other security focal point) will also have phone numbers for all team members |
|  | Daily Debrief: Team coordinator leads team debriefs at the beginning and during set intervals during the assessment |
|  | Movement Plan: Ensure team members are aware of the time of departure and return each day |
| Logistics & Security |  |
|  | Security & Coordination: A meeting area will be determined each morning by assessment team leaders and will be revised each morning, as appropriate and necessary |
|  | Transport: Adequate vehicles will be requested through logistics available to travel to the assessment sites and stay on-site through the entire day |
| Supplies |  |
|  | Water & Snacks: Each car/team should have sufficient safe drinking water and snacks for the day |
|  | Assessment Forms: Copy or print multiple copies of the assessment forms that have been adapted by the team in advance |
|  | Excel Database: Develop a tool that can be used to organize and compile assessment information into one place |
|  | Pens, Notebooks & Folders: All assessment team members should carry several pens and a notebook |
|  | Time-Keeping: Ensure team members have a watch or cell phones so that they can keep time |
|  | Identification: Ensure all team members have badges with a way to make them visible |
|  | Clipboards: When using the actual assessment forms, clipboards may be useful |
|  | Clear Plastic Pouches: Plastic envelope for holding forms and paper |
| Other Preparations |  |
|  | Discussion with Local Authorities: The team coordinator will organize a discussion with relevant authorities so they understand the purpose and process of the assessment, and give appropriate approval |
|  | Service Availability & Referrals: Document the referral plan and procedures for survivors who may report their cases according to services available in the area |